## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Alec | David | Kendal | Joshua | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Overview |  |  |  |  | 4 |  | 4 | 1 | 1 | 1 | 1 | 4
|  | Design Project Plan | Project Manager | Alec, David, Kendal, Joshua | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
| Requirements |  |  |  |  | 9 |  | 9 | 2.25 | 2.25 | 2.25 | 2.25 | 9
|  | Usage of Required Communication Outlets | All | Alec, David, Kendal, Joshua | 1 |  | 1 |  | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  | Analyze Requirements | All | Alec, David, Kendal, Joshua | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Determine strengths/assign roles | All | Alec, David, Kendal, Joshua | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Schedule Meet Up Times/Days (Agile) | All | Alec, David, Kendal, Joshua | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
| Documentation |  |  |  |  | 27 |  | 23 | 4.5 | 3 | 8.5 | 7 | 23
|  | Project Charter | Project Manager | Kendal | 2 |  | 3 |  |  |  | 3 |  | 3
|  | Risk Managment Document | Project Manager | Kendal | 2 |  | 2 |  |  |  | 2 |  | 2
|  | Requirements Document | Project Manager, Requirements Engineer | Joshua | 4 |  | 4 |  |  |  |  | 4 | 4
|  | Project Plan | Project Manager, Developers | David, Kendal, Joshua, Alec | 8 |  | 11 |  | 3 | 3 | 2 | 3 | 11
|  | Architecture Document | Architect, Developers | Kendal, Alec | 3 |  | 3 |  | 1.5 |  | 1.5 |  | 3
|  | Test Plan | Developers, Tester | Joshua | 3 | [7 empty] | 0
|  | User and System Guide | Developers, Requirements Engineer | Joshua, Kendal | 5 | [7 empty] | 0
Forming | Development |  |  |  |  | 23 |  | 30.5 | 6.5 | 7 | 6.5 | 10.5 | 30.5
Iteration 1: |  | Design Overall Scope and Objectives | Project Manager, Developers | Alec, Kendal, Joshua | 3 |  | 3 |  | 1 |  | 1 | 1 | 3
|  | Determine Desired Technologies | Developer, Project Manager | Alec, David, Kendal, Joshua | 4 |  | 5.5 |  | 1.5 | 1 | 1.5 | 1.5 | 5.5
|  | Read/Understand Documentation on New Technologies | Developer | Alec, David, Kendal, Joshua | 10 |  | 16 |  | 4 | 4 | 4 | 4 | 16
|  | Design Database Requirements | Developer | Joshua, David | 6 |  | 6 |  |  | 2 |  | 4 | 6
| Analysis |  |  |  |  | 7 |  | 9 | 1.5 | 2.5 | 2.5 | 2.5 | 9
|  | Prepare for next iteration | Project Manager, Developers | Alec, David, Kendal, Joshua | 4 |  | 6 |  | 1.5 | 1.5 | 1.5 | 1.5 | 6
|  | Finalize Present Iteration | Project Manager, Developers | Kendal, Joshua, David | 3 |  | 3 |  |  | 1 | 1 | 1 | 3
Planning | Design |  |  |  |  | 24 |  | 22.5 | 8.5 | 0 | 4 | 10 | 22.5
Iteration 2: |  | Design High Level Front End Design | Developers | Alec, Joshua | 6 |  | 6 |  | 3 |  |  | 3 | 6
|  | Design Models and Relationships | Architect, Developers | Joshua, Alec,David | 8 |  | 8 |  | 3 |  | 2 | 3 | 8
|  | Design Checking Process | Architect, Developers | Alec, Joshua, David | 4 |  | 3 |  |  |  | 1.5 | 1.5 | 3
|  | Draw Prototypes for Further Development | Architect, Developers | Alec, Josh | 4 |  | 4 |  | 2 |  |  | 2 | 4
|  | Design Schedule Checking Process | Architect, Developers | Joshua, Alec, David | 2 |  | 1.5 |  | 0.5 |  | 0.5 | 0.5 | 1.5
| Development |  |  |  |  | 1 |  | 1 | 1 | 0 | 0 | 0 | 1
|  | Starting Creating Technical UI | Developer | Alec | 1 |  | 1 |  | 1 |  |  |  | 1
| Analysis |  |  |  |  | 12 |  | 14 | 3 | 2 | 3 | 6 | 14
|  | Create First Presentation for Client | Project Manager, Developers | Joshua, David, Alec | 6 |  | 8 |  | 3 | 2 |  | 3 | 8
|  | Prepare for Next Iteration | Project Manager, Developers | Joshua, Kendal | 4 |  | 4 |  |  |  | 2 | 2 | 4
|  | Finalize Present Iteration | Project Manager, Developers | Joshua, Kendal | 2 |  | 2 |  |  |  | 1 | 1 | 2
Implemenation | Design |  |  |  |  | 6 |  | 6 | 1.5 | 1.5 | 0 | 3 | 6
Iteration 3: |  | Design specific data models | Developers | David, Joshua | 3 |  | 3 |  |  | 1.5 |  | 1.5 | 3
|  | Design conflict rule model | Architect, Developers | Joshua, Alec | 3 |  | 3 |  | 1.5 |  |  | 1.5 | 3
| Development |  |  |  |  | 4 |  | 4 | 4 | 0 | 0 | 0 | 4
|  | Create basic user interface based on design | Developers | Alec | 4 |  | 4 |  | 4 |  |  |  | 4
| Analysis |  |  |  |  | 6 |  | 6 | 1.5 | 0 | 0 | 4.5 | 6
|  | Prepare for Next Iteration | Project Manager, Developers | Alec, Joshua | 4 |  | 4 |  | 1 |  |  | 3 | 4
|  | Finalize Present Iteration | Project Manager, Developers | Alec, Joshua | 2 |  | 2 |  | 0.5 |  |  | 1.5 | 2
Implementation | Design |  |  |  |  | 6 |  | 3 | 1.5 | 0 | 0 | 1.5 | 3
Iteration 4: |  | Design specific data models | Developers | Joshua, Alec | 3 |  | 3 |  | 1.5 |  |  | 1.5 | 3
|  | Design conflict rule model | Architect, Developers | Joshua, Kendal, Alec | 3 | [7 empty] | 0
| Development |  |  |  |  | 16 |  | 13 | 6 | 0 | 0 | 7 | 13
|  | Create basic user interface based on design | Developers | Alec | 4 |  | 4 |  | 4 |  |  |  | 4
|  | Add unit testing framework | Developers, Tester | Kendal, Alec | 2 |  | 1 |  | 1 |  |  |  | 1
|  | Implement database connection | Developers | Joshua, Alec | 2 |  | 2 |  | 1 |  |  | 1 | 2
|  | Implement database schemas | Developers | Joshua | 8 |  | 6 |  |  |  |  | 6 | 6
| Analysis |  |  |  |  | 6 |  | 6 | 0 | 0 | 2 | 4 | 6
|  | Prepare for Next Iteration | Project Manager, Developers | Joshua, Kendal | 4 |  | 4 |  |  |  | 1 | 3 | 4
|  | Finalize Present Iteration | Project Manager, Developers | Joshua, Kendal | 2 |  | 2 |  |  |  | 1 | 1 | 2
Implementation/ Testing | Design |  |  |  |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0
Iteration 5: |  | Design conflict rule model | Architect, Developers | Joshua, Kendal, Alec | 3 | [7 empty] | 0
0
| Development |  |  |  |  | 14 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Create basic user interface based on design | Developers | Alec | 6 | [7 empty] | 0
|  | Implement backend database interface | Developers | Alec | 8 | [7 empty] | 0
0
0
0
0
| Analysis |  |  |  |  | 18 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Finalize Present Iteration | Project Manager, Developers | Alec, Kendal, Joshua | 4 | [7 empty] | 0
|  | Create Final Presentation | Project Manager, Developers | Alec, Kendal, Joshua | 6 | [7 empty] | 0
|  | System Testing | Tester, Developer | Alec, Kendal, Joshua | 4 | [7 empty] | 0
|  | Bug fix from testing results | Tester, Developer | Alec, Kendal, Joshua | 4 | [7 empty] | 0
0
Total | [5 empty] | 186 |  | 151 | 42.75 | 19.25 | 29.75 | 59.25 | 151
Total |  |  |  |  | 0 | 0 | 0 | 0