## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Alec | David | Kendal | Joshua
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Overview |  |  |  |  | 4 |  | 0
|  | Design Project Plan | Project Manager | Alec, David, Kendal, Joshua | 4
| Requirements |  |  |  |  | 9 |  | 0 |  |  |  |  | 0
|  | Usage of Required Communication Outlets | All | Alec, David, Kendal, Joshua | 1
|  | Analyze Requirements | All | Alec, David, Kendal, Joshua | 4
|  | Determine strengths/assign roles | All | Alec, David, Kendal, Joshua | 2
|  | Schedule Meet Up Times/Days (Agile) | All | Alec, David, Kendal, Joshua | 2
| Documentation |  |  |  |  | 19 |  | 0 |  |  |  |  | 0
|  | Project Charter | Project Manager | Kendal | 2
|  | Release Plan | Project Manager | Joshua, | 2
|  | Requirements Document | Project Manager, Requirements Engineer | Kendal, Joshua | 4
|  | Project Plan | Project Manager, Developers | David | 2
|  | Architecture Document | Architect, Developers | Kendal | 3
|  | Test Report | Developers, Tester | David, Alec | 2
|  | User Guide/Admin Doc | Developers, Requirements Engineer | Kendal, Joshua | 4
Coding | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 44 |  | 0 |  |  |  |  | 0
|  | Determine Desired Technologies | Developer, Project Manager | Alec, David, Kendal, Joshua | 4
|  | Read/Understand Documentation on New Technologies | Developer | Alec, David, Kendal, Joshua | 10
|  | Design Database Requirements | Developer | Joshua, David | 6
|  | Implement Database Structure | Developer | Joshua, David | 15
|  | Design High Level Front End Design | Developer | Joshua, Alec | 4
|  | Create Basic UI for Further Development | Developer | Kendal, Alec | 3
|  | Design Unit Testing | Developer, Tester | Kendal, Alec | 2
| Analysis |  |  |  |  | 12 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester, Developer | Kendal | 4
|  | Bug fix from testing results | Tester, Developer | Alec | 4
|  | Prepare for next iteration | Project Manager, Developers | Alec, David, Kendal, Joshua | 4
Iteration 2: | Design |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
Iteration 3: | Design |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0